## SprintPlan
Sprint | Weeks | Focus Area | Epics | Stories | Status
Sprint 0 | 1 | Foundation, Infra, DevOps | 2 | 8 | MVP
Sprint 1 | 2 | Auth + Landing + Merchants | 3 | 12 | MVP
Sprint 2 | 2 | Product Catalog + Search | 3 | 10 | MVP
Sprint 3 | 2 | Cart + Checkout + Payments | 4 | 14 | MVP
Sprint 4 | 2 | WhatsApp + Tracking + Profile | 3 | 10 | MVP
Sprint 5 | 2 | Merchant Dashboard + Admin | 3 | 12 | MVP
Sprint 6 | 1 | QA, Staging, Launch Prep | 2 | 8 | MVP
Sprint 7 | 2 | Mobile App Parity | 2 | 10 | Post-MVP
Sprint 8 | 2 | AI Reels + Analytics | 2 | 8 | Post-MVP
Sprint 9 | 2 | Marketing + SEO + Onboarding | 3 | 10 | Post-MVP
Sprint 10 | 2 | Multi-City Prep | 2 | 7 | Post-MVP
Sprint 11 | 2 | Polishing + Production Launch | 2 | 6 | Post-MVP

## EpicMap
Epic | Category | Stories | Sprint Range | Priority
E1: Platform Foundation | Infra | 5 | Sprint 0 | P0
E2: Auth & Personas | Auth | 6 | Sprint 1 | P0
E3: Customer Landing | UI/UX | 4 | Sprint 1 | P0
E4: Merchant Discovery | UI/UX | 6 | Sprint 1-2 | P0
E5: Product Catalog | Backend | 8 | Sprint 2 | P0
E6: Search & Filter | API | 5 | Sprint 2 | P0
E7: Shopping Cart | Commerce | 6 | Sprint 3 | P0
E8: Checkout Flow | Commerce | 5 | Sprint 3 | P0
E9: Payments | Commerce | 4 | Sprint 3 | P0
E10: WhatsApp Integration | API | 5 | Sprint 4 | P0
E11: Order Tracking | UI/UX | 4 | Sprint 4 | P0
E12: Merchant Dashboard | UI/UX | 6 | Sprint 5 | P0
E13: Admin Console | UI/UX | 6 | Sprint 5 | P0
E14: QA & Staging | Infra | 5 | Sprint 6 | P0
E15: Mobile App | Mobile | 8 | Sprint 7 | P1
E16: AI Content | AI | 6 | Sprint 8 | P1
E17: Analytics | Backend | 5 | Sprint 8 | P1
E18: Marketing Pages | UI/UX | 4 | Sprint 9 | P1
E19: Merchant Onboarding | Backend | 4 | Sprint 9 | P1
E20: Multi-City | Infra | 5 | Sprint 10 | P2
E21: Polish & Launch | All | 4 | Sprint 11 | P0