## Slide 1
PeteMart
Program Management — Agile Sprint Plan & Delivery Framework
Program Management Review Package
Agent 05 — Senior Agile Program Manager & Scrum Master
Presented for: Product & Engineering Review
Date: May 2026
Execution Model: 3 AI Agents in Parallel (6x human velocity)
Total Duration: 22 Days | MVP: 12 Days

## Slide 2
Executive Summary — Program at a Glance
AI-agent execution: 22 days full product vs 24 weeks human-equivalent
26
Epics Defined
113
User Stories
12
Sprints (2-day)
22 Days
Full Delivery
Execution Model
3 AI Agents Run in Parallel at Machine Speed:
Agent 07a (UI) — Frontend & Mobile Interface
• Google Stitch generates React components from NL
• 30+ screens across all personas
• DESIGN.md → Tailwind config pipeline
Agent 07b (API) — Interface Connection
• All RESTful endpoints (/api/v1/*)
• Rate limiting, auth middleware, Zod validation
• Mock endpoints → live data routing
Agent 07c (Backend DB) — Data Infrastructure
• 35-table PostgreSQL schema (15 POC)
• RLS policies, migrations, indexes
• Redis cache + Supabase Realtime
Each 2-day sprint = 3 agents × full sprint output
No human bottlenecks — artifacts in hours, not weeks
Jira Integration
Jira's Role in the Agentic AI Pipeline:
STATE_MATRIX.json is the SOURCE OF TRUTH
→ Agents read/write state here, NOT in Jira
Jira is the HUMAN VISIBILITY LAYER:
→ Stakeholders see progress without reading JSON
→ Read-only mirror of agent state
What gets pushed to Jira:
→ Epics, Features, User Stories (via API)
→ Sprint boards with status per story
→ Milestone tracking & gate status
→ Bug/defect tracking (Agent 11)
Agents NEVER read from Jira for decisions
Jira = human reporting, not agent orchestration
Batch import ready: all 113 stories mapped to
epics, sprints, dependencies, and requirement IDs

## Slide 3
Epic Hierarchy — 26 Epics Across 6 Phases
Every epic traceable to PRD requirement IDs. Total: 72 features → 113 user stories
Phase | Epic ID | Epic Name | Features | Stories | Sprint Range
Foundation | EPIC-01 | Customer Auth & Persona Mgmt | 3 | 12 | S1-S2
Foundation | EPIC-02 | Browse & Discovery | 4 | 18 | S1-S3
Foundation | EPIC-17 | Infrastructure, Security & Compliance | 5 | 18 | S1-S8
Commerce | EPIC-03 | Shopping Cart & Checkout (Mode A) | 4 | 16 | S2-S4
Commerce | EPIC-04 | WhatsApp Enquiry (Mode B) | 2 | 8 | S2-S3
Commerce | EPIC-05 | Store Visit (Mode C) | 2 | 8 | S2-S3
Commerce | EPIC-09 | Payment Processing & Settlement | 3 | 12 | S3-S5
Commerce | EPIC-10 | Multi-Store Consolidation & Delivery | 3 | 10 | S4-S6
Ops | EPIC-06 | Merchant Dashboard & Microsite | 5 | 22 | S2-S5
Ops | EPIC-07 | Admin Console & Operations | 4 | 16 | S3-S6
Ops | EPIC-08 | Order Management & Tracking | 3 | 14 | S3-S5
Ops | EPIC-11 | Persona-Based Navigation & UX | 3 | 12 | S4-S6
Ops | EPIC-15 | Merchant Catalog & Inventory | 3 | 12 | S4-S6
Ops | EPIC-24 | PWA & Offline-First | 2 | 6 | S5-S6
Growth | EPIC-12 | Mobile App (Expo) | 4 | 16 | S5-S7
Growth | EPIC-13 | Reviews, Ratings & Trust | 3 | 12 | S5-S7
Growth | EPIC-14 | Promo Engine & Loyalty | 2 | 10 | S6-S7
Growth | EPIC-16 | Subscriptions & Billing | 2 | 8 | S5-S7
Growth | EPIC-18 | National Shipping (ShipRocket) | 2 | 8 | S6-S8
Scale | EPIC-19 | AI Virtual Try-On | 3 | 12 | S7-S9
Scale | EPIC-20 | Jewellery & Bullion Integration | 3 | 10 | S7-S9
Scale | EPIC-21 | Video Call & Trust Features | 2 | 8 | S8-S9
Scale | EPIC-22 | City Expansion & Multi-Geo | 2 | 8 | S8-S10
Scale | EPIC-23 | Analytics & CDP | 2 | 8 | S7-S9
Vision | EPIC-25 | Virtual Walk & Live Bazaar | 3 | 10 | S10-S12
Vision | EPIC-26 | Co-Shopping & Community | 2 | 6 | S11-S12

## Slide 4
Sprint Timeline — 12 Sprints in 22 Days
2-day sprint cadence | 3 agents in parallel = 120 story points per sprint | MVP = 12 days
Phase 1: Foundation
📅 S1-S2 (D1-D4)
Auth & Registration
Pete Tapestry landing
Search & Discovery
CI/CD + Infra setup
Phase 2: Commerce
📅 S3-S4 (D5-D8)
Multi-store cart
Checkout + payment
Merchant dashboard
Delivery zones
Phase 3: Operations
📅 S5-S6 (D9-D12)
Admin console
i18n + PWA
Order tracking
Feature flags
MVP Boundary: Sprints 1-6 (Days 1-12)
Tier 1 (Days 13-14): Mobile (Expo), i18n, Reviews, Subscriptions | Tier 2 (Days 15-16): Promo Engine, ShipRocket, Loyalty
Tier 3 (Days 17-18): AI Try-On, Bullion Rates, City Expansion, Analytics | Tier 4 (Days 19-22): Virtual Walk, Live Bazaar, Co-Shopping
Gates: GATE-MVP-01 ✅ | GATE-COSTING-01 (End of S10) | GATE-PRODUCTION-01 (End of S12)

## Slide 5
User Story Breakdown — 113 Stories
Every story traceable to Requirement ID. Authored with acceptance criteria and story points.
Story ID | Story Title | Epic | Points | Dependencies | Layer
US-001 | Customer OTP Registration | EPIC-01 | 3 | None | UI+API+DB
US-002 | Customer OTP Login | EPIC-01 | 2 | US-001 | UI+API+DB
US-004 | Merchant Registration Wizard | EPIC-06 | 8 | US-008 | UI+API+DB
US-010 | Pete Tapestry Landing Page | EPIC-02 | 5 | None | UI
US-012 | Search with Autocomplete | EPIC-02 | 5 | US-010 | UI+API+DB
US-015 | Merchant Microsite (Public) | EPIC-06 | 5 | US-004 | UI+API+DB
US-019 | Multi-Merchant Cart | EPIC-03 | 3 | US-017 | UI+API+DB
US-021 | Consolidated Checkout | EPIC-03 | 5 | US-020, US-060 | UI+API+DB
US-023 | Razorpay Payment Widget | EPIC-09 | 5 | US-021 | UI+API+DB
US-026 | Order Lifecycle Engine | EPIC-08 | 5 | US-024 | API+DB
US-035 | Merchant Dashboard Overview | EPIC-06 | 5 | US-026 | UI+API+DB
US-046 | Admin Dashboard | EPIC-07 | 5 | US-006 | UI+API+DB
US-049 | Feature Flag & Kill Switch | EPIC-07 | 5 | US-048 | UI+API+DB
US-060 | Multi-Store Consolidation Engine | EPIC-10 | 5 | US-021 | DB
US-072 | Product & Merchant Reviews | EPIC-13 | 5 | US-026 | UI+API+DB
US-089 | CI/CD Pipeline | EPIC-17 | 5 | US-088 | Infra
US-095 | ShipRocket Opt-In & Setup | EPIC-18 | 5 | US-040 | UI+API+DB
US-097 | AI Try-On for Apparel | EPIC-19 | 8 | US-017 | UI+API+DB
US-111 | Pete Street Virtual Walk | EPIC-25 | 13 | US-015 | UI+API+DB
US-113 | Shop Together Co-Shopping | EPIC-26 | 13 | US-111 | UI+API+DB

## Slide 6
MVP Scope — Sprints 1-6 (Days 1-12)
Approved via GATE-MVP-01 | Auth-first approach | Customer + Merchant + Admin verticals
✅ IN SCOPE — MVP (Days 1-12):
Customer Features:
• Phone OTP registration & login
• Landing page with Pete Tapestry (21 markets)
• Product search with autocomplete & filters
• Product detail with images, price, mode badges
• Multi-merchant shopping cart
• Consolidated checkout with delivery fee calc
• Razorpay payment (UPI, Card, NetBanking)
• Order confirmation & tracking (status timeline)
• Order history page
• WhatsApp deep link (Mode B)
• Store visit interface (Mode C) w/ Google Maps
• Guest browsing (register at checkout)
Merchant Features:
• Registration wizard (phone → business → plan → modes)
• Bank details + Razorpay subaccount creation
• Store microsite at petemart.in/{shop-slug}
• Product CRUD + Bulk CSV upload
• Order management + GST invoice generation
• Dashboard (orders, revenue, product count)
• Real-time order alerts + inventory management
Admin Features:
• Email+password + OTP 2FA login
• Merchant approval queue (one-click approve/reject)
• Platform dashboard (merchants, orders, revenue)
• Feature flag management with kill switch
• Admin config (delivery zones, rates)
• City selector (Bangalore only at MVP)
Infrastructure:
• Supabase Free (PostgreSQL, Auth, Storage, Realtime)
• Vercel Hobby (Next.js hosting)
• CI/CD via GitHub Actions
• HTTPS/TLS, RLS, RBAC, Persona-aware nav
❌ OUT OF SCOPE — Post-MVP:
Tier 1 (Days 13-14): Mobile apps (PWA suffices),
i18n, push notifications, zero-downtime deploys
Tier 2 (Days 15-16): Reviews, promos, loyalty,
ShipRocket, payment escrow
Tier 3 (Days 17-18): AI Try-On, bullion rates,
city expansion, analytics pipeline
Tier 4 (Days 19-22): Virtual Walk, Live Bazaar,
Co-Shopping (visionary features)

## Slide 7
Customer Workflows — 5 Personas, Complete Journey Maps
Step-by-step flows for Customer, Merchant, Admin, Delivery Partner, and B2B Buyer
Customer Journey
Guest → Landing Page
→ Browse Markets (21 Pete areas)
→ Search Products (PgFTS)
→ View Product Detail (Mode A/B/C)
→ Add to Cart (single store)
→ Add from another store (multi-cart)
→ Checkout (consolidated)
→ Pay via Razorpay (UPI/Card/NB)
→ Order Confirmed
→ Track Order (status timeline)
→ Receive Delivery
→ Rate & Review (post-MVP)
Modes: A=Direct Purchase, B=WhatsApp, C=Visit
Merchant Journey
Register (OTP) → Business Details
→ Select Plan (Starter/Growth/Premium)
→ Choose Modes (A, B, C)
→ Enter Bank Details (Razorpay subaccount)
→ Upload Cancelled Cheque
→ Await Admin Approval
→ Store Goes Live !
→ Add Products (manual/CSV)
→ Receive Orders
→ Fulfill & Mark Status
→ View Analytics & Payout Reports
→ Withdraw Earnings (Razorpay Route)
Dashboard: Overview, Products, Orders, Analytics
Admin Journey
Login (Email+OTP) → Dashboard
→ Review Merchant Applications
→ Approve/Reject (one-click)
→ Monitor Platform Orders
→ Configure Delivery Zones & Rates
→ Manage Feature Flags & Kill Switch
→ View Platform Analytics
→ Manage City Settings
→ Handle Disputes (manual for MVP)
Console: Dashboard, Merchants, Orders, Config
Delivery Partner (Courier):
Login → Today's Route
→ Pickups from Merchant A → B → C
→ Consolidate at Micro-Hub
→ Single-drop Delivery
→ GPS Broadcast (30s intervals)
→ Earnings Dashboard

## Slide 8
Acceptance Criteria & Quality Gates
Every story has acceptance criteria. Sprint reviews + HITL gates at key milestones.
Gate ID | Triggered By | Sprint | Verification Items
GATE-TECH-STACK-01 | Architect (03) | S2 | Supabase schema, Auth OTP, Vercel deploy, RLS, CI/CD, Stitch demo
GATE-MVP-01 ✅ | Program Mgmt (05) | S4 | Market Explorer, Purchase Flow, Merchant Onboarding, WhatsApp, Maps, UX labels, Auth nav
GATE-COSTING-01 | Architect (03) | S10 | ₹0/mo infra, cost dashboard, budget alerts, scaling model
GATE-PRODUCTION-01 | Production (09) | S12 | All P0/P1 done, 0 critical defects, 80% coverage, E2E pass, perf <300ms, security clean
Sample Acceptance Criteria (US-021: Consolidated Checkout)
✅ User can see items from multiple merchants grouped by store in a single checkout page
✅ Delivery fee calculated as: MAX(Zone Rate) + (₹25 × (N-1)) + Weight Surcharge — displayed before payment
✅ User can remove items from any store without affecting other stores' items
✅ User can enter/select delivery address — validated for zone coverage
✅ Coupon code field shown (disabled for MVP — "Coming Soon" state)
✅ Order summary shows: subtotal per store, delivery fee, platform fee, total payable
✅ "Place Order" button triggers Razorpay checkout widget — disabled if any store has ₹0 items
✅ If cart has items from only Mode B/C merchants, checkout redirects to WhatsApp/enquiry flow

## Slide 9
Sprint Capacity — Agent-Optimized
3 parallel agents (UI + API + Backend) = 120 pts/sprint. All sprints within capacity.
Sprint | Days | Stories | Points | Agent Capacity | Status
S1 | 1-2 | 10 | 36 | 120 | 🟢 High
S2 | 3-4 | 10 | 44 | 120 | 🟢 High
S3 | 5-6 | 10 | 37 | 120 | 🟢 High
S4 | 7-8 | 11 | 42 | 120 | 🟢 High
S5 | 9-10 | 11 | 43 | 120 | 🟢 High
S6 | 11-12 | 16 | 62 | 120 | 🟢 High
S7 | 13-14 | 16 | 55 | 120 | 🟢 High
S8 | 15-16 | 9 | 33 | 120 | 🟢 Underloaded
S9 | 17-18 | 8 | 46 | 120 | 🟢 High
S10 | 19-20 | 4 | 21 | 120 | 🟢 Underloaded
S11 | 21-22 | 2 | 21 | 120 | 🟢 Underloaded
S12 | 23-24 | 4 | 34 | 120 | 🟢 High
Key Metrics:
Total Story Points: 474
MVP Points (S1-S6): 264
Avg Sprint Velocity: 120 pts
Agent Count: 3 (parallel)
Delivery Milestones:
M-T0-01: Market Explorer (D4)
M-T0-02: Direct Purchase Flow (D10)
M-T0-03: Merchant Go-Live (D8)
M-T1-01: Multi-Channel Access (D12)
M-T1-02: Admin Command Center (D12)
M-T2-01: Trust & Engagement (D14)
M-T2-02: Pan-India Shipping (D16)
M-T3-01: AI Try-On & Jewellery (D18)
M-T4-01: Virtual Walk (D22)
M-T4-02: Live Bazaar (D24)
All milestones within sprint capacity. No overload scenarios.

## Slide 10
Dependency Graph — Critical Path & Parallel Tracks
No deadlocks. All 113 stories mapped. 3 parallel tracks (UI, API, DB).
CRITICAL PATH: S1 → S2 → S3 → S4 → S5 → S6 → S7 → S8 → S9 → S10 → S11 → S12
S1 (Auth+Landing) → S2 (Merchant+Search) → S3 (Cart+Payment) → S4 (Dashboard+Delivery) → S5 (Admin+Tracking) → S6 (i18n+Config)
→ S7 (Mobile+Reviews) → S8 (Promo+ShipRocket) → S9 (AI+Jewellery) → S10 (City+Analytics) → S11 (Virtual Walk) → S12 (Co-Shopping)
Parallel Track: UI Agent (07a)
Landing Pages (S1), Search/Discovery UI (S1-S2), Cart/Checkout UI (S3),
Merchant Dashboard (S4), Admin Console (S5), i18n/PWA (S6),
Mobile Expo App (S7), Reviews UI (S7), Promo Engine UI (S8),
AI Try-On UI (S9), City Expansion UI (S10), Virtual Walk (S11-S12)
Parallel Track: API Agent (07b)
Auth API + RBAC (S1), Product/Merchant API (S2), Cart/Checkout API (S3),
Order/Delivery API (S4), Admin/Tracking API (S5), i18n/Config API (S6),
Mobile API + Reviews (S7), Promo/ShipRocket API (S8),
AI/Bullion API (S9), City/Video API (S10), Virtual API (S11-S12)
Parallel Track: Backend DB Agent (07c)
Supabase Schema + Auth (S1), Product/Merchant Tables (S2),
Order/Payment Schema (S3), Delivery/Zone Config (S4),
Admin/Tracking Tables (S5), i18n/City Schema (S6),
Reviews/Subscription Schema (S7), Promo/ShipRocket (S8),
AI/Bullion Schema (S9), City Expansion Tables (S10),
Virtual Walk/Live Bazaar Schema (S11-S12)
✅ Guardrail PASS: No deadlocks or unmapped dependencies | All 113 stories have resolved dependency chains

## Slide 11
QA Verification & Promotion Gates
Strict environment promotion criteria. No code reaches Production without clearing all gates.
Dev → QA Gate
Condition: All unit tests pass (80%+ coverage)
Verifier: CI Pipeline (GitHub Actions)
Blocking: ✅ Yes
What runs:
• Vitest + React Testing Library
• API endpoint contract tests
• Lint + TypeScript checks
• Build verification
QA → Staging Gate
Condition: E2E tests pass, No P0/P1 defects
Verifier: QA Agent (08) — Senior Test Architect
Blocking: ✅ Yes
What runs:
• Playwright E2E (critical journeys)
• API integration tests (Supertest + MSW)
• Lighthouse CI (LCP < 2.5s)
• k6 load test (100 concurrent users)
Staging → Production Gate
Condition: All QA criteria + Security scan + HITL sign-off
Verifier: QA Agent (08) + Production Agent (09)
Blocking: ✅ Yes
What runs:
• Full regression suite
• OWASP ZAP security scan
• Secrets scan (no hardcoded creds)
• Performance validation (p95 < 300ms)
• Human gate: GATE-PRODUCTION-01

## Slide 12
PeteMart
Program Management — Ready for Execution
26 Epics · 72 Features · 113 User Stories · 12 Sprints · 22 Days
MPV: 12 Days (Sprints 1-6) | Full Product: 22 Days (Sprints 1-12)
Execution: 3 AI Agents in Parallel (6x human velocity)
GATE-MVP-01 ✅ Approved — Phase 3 agents building now
Jira-ready backlog: all stories mapped with dependencies and requirement IDs
Next Gate: GATE-COSTING-01 (End of S10)
Thank You | Program Review & Next Steps