## Epic Registry
PeteMart — Epic Registry
Epic ID | Epic Name | Business Goal | Version | MoSCoW | Owner | Story Count
E01 | Identity & Access Management | Secure, frictionless auth for all 3 user roles | MVP | Must | Auth Team | 5
E02 | Merchant Onboarding & Store Setup | Enable any pete-area business to go live in <30 min | MVP | Must | Product + Design | 5
E03 | Product Catalog & Content | Rich product listings with reels, variants, pricing tiers | MVP | Must | Product + Dev | 6
E04 | Inventory Management | Real-time stock control with alerts and audit trail | MVP | Must | Backend Dev | 3
E05 | Customer Discovery & Search | Help buyers find the right product and store fast | MVP | Must | Search + Frontend | 5
E06 | Cart, Checkout & Payments | Frictionless multi-store purchase with Razorpay | MVP | Must | Payments + Dev | 4
E07 | Order Management & Fulfillment | End-to-end order lifecycle for buyer and seller | MVP | Must | Backend + Ops | 5
E08 | Analytics & Business Intelligence | Data-driven decisions for sellers and platform | v1.0 | Should | Data + Backend | 4
E09 | Social Commerce & Reels | Reel-driven product discovery and social handle integration | v1.5 | Should | Content + Dev | 3
E10 | Promotions & Growth Engine | Discounts, coupons, ads, loyalty to drive GMV | v1.5 | Should | Product + Marketing | 3
E11 | Admin & Platform Operations | Full platform governance, moderation, billing control | MVP | Must | Admin + Ops | 5
E12 | Mobile Apps (Customer + Seller) | Native iOS/Android experience for buyers and merchants | v2.0 | Could | Mobile Dev | 2

## Product Backlog
PeteMart — Full Product Backlog (50 Stories)
Epic ID | Story ID | Story Title | Given | When | Then | Acceptance Criteria | Tasks | Portal | Business Impact | MoSCoW | Version | Blocks | Blocked By | Owner
E01 | US-001 | Customer Mobile OTP Login | Given I am a new or returning customer | When I enter my mobile number and receive an OTP | Then I am authenticated and land on the home feed | 1. OTP delivered in <5s via MSG91 2. 3 retry attempts allowed 3. Session valid for 30 days 4. Invalid OTP shows clear error | 1. Integrate MSG91 OTP API 2. Build OTP input UI 3. JWT session management 4. Resend timer (30s) 5. Unit tests | Customer | Critical | Must | MVP | US-019 | — | Auth Dev
E01 | US-002 | Customer Google OAuth Login | Given I am a customer who wants quick login | When I tap "Continue with Google" | Then I am authenticated using my Google account | 1. Google OAuth 2.0 flow works 2. Profile auto-filled from Google 3. Existing account linked if mobile matches | 1. Google OAuth SDK integration 2. Account merge logic 3. Profile auto-populate 4. Unit tests | Customer | High | Must | MVP | — | US-001 | Auth Dev
E01 | US-003 | Seller Mobile OTP Login | Given I am a registered seller | When I log in with my registered mobile OTP | Then I land on my seller dashboard | 1. Same OTP flow as customer 2. Role-based redirect to seller dashboard 3. Inactive store shows reactivation prompt | 1. Role detection post-auth 2. Seller dashboard redirect 3. Inactive store state handling | Seller | Critical | Must | MVP | US-004 | US-001 | Auth Dev
E01 | US-004 | Admin Login (Email + Password + 2FA) | Given I am a PeteMart admin | When I log in with email, password, and 2FA code | Then I access the admin panel | 1. 2FA via TOTP (Google Authenticator) 2. Failed login lockout after 5 attempts 3. Audit log of admin logins | 1. Admin credential store 2. TOTP integration 3. Lockout logic 4. Audit log table | Admin | Critical | Must | MVP | — | US-001 | Auth Dev
E01 | US-005 | Password Reset Flow | Given a user forgot their password | When they request reset via mobile/email | Then they receive a reset link/OTP and can set a new password | 1. Reset link expires in 15 min 2. Old sessions invalidated after reset 3. Confirmation message shown | 1. Reset token generation 2. Email/SMS dispatch 3. Token expiry logic 4. Session invalidation | All | Medium | Must | MVP | — | US-001 | Auth Dev
E02 | US-006 | Seller Self-Registration | Given I am a pete-area business owner | When I fill the registration form with business details | Then my application is submitted for admin review | 1. Required: name, mobile, business name, area, category 2. Duplicate mobile check 3. Application confirmation SMS sent 4. Status visible in seller app | 1. Registration form UI 2. Duplicate check API 3. Application DB record 4. SMS confirmation 5. Admin notification | Seller | Critical | Must | MVP | US-007 | US-003 | Product Dev
E02 | US-007 | KYC Document Upload | Given my registration is submitted | When I upload my KYC documents (Aadhaar/GSTIN/Shop License) | Then my documents are stored securely and sent for review | 1. Accepts PDF/JPG/PNG up to 5MB 2. Documents stored in S3 with encryption 3. Upload progress shown 4. Re-upload allowed if rejected | 1. File upload component 2. S3 integration with encryption 3. Document status tracking 4. Admin review queue trigger | Seller | Critical | Must | MVP | US-008 | US-006 | Backend Dev
E02 | US-008 | Store Profile Setup | Given my KYC is approved | When I set up my store profile | Then my branded virtual storefront is live on PeteMart | 1. Required: store name, logo, banner, area, category 2. Optional: tagline, WhatsApp, Instagram, YouTube, Facebook 3. Store slug auto-generated from store name 4. Preview before publish | 1. Store profile form 2. Image upload + crop tool 3. Slug generator 4. Social handle input + validation 5. Store preview page 6. Go-live toggle | Seller | Critical | Must | MVP | US-009 | US-007 | Product + Design
E02 | US-009 | Subscription Plan Selection & Payment | Given my store is set up | When I choose a subscription plan (Starter/Growth/Premium) | Then I am billed via Razorpay and my store is activated | 1. Plan comparison page shown 2. Razorpay subscription created 3. Payment confirmation triggers store activation 4. Invoice emailed 5. Trial period (14 days) before billing if applicable | 1. Plan selection UI 2. Razorpay subscription API integration 3. Webhook for payment confirmation 4. Store activation trigger 5. Invoice PDF generation 6. Email dispatch | Seller | Critical | Must | MVP | US-010 | US-008 | Payments Dev
E02 | US-010 | Admin Merchant Approval Workflow | Given a new seller has submitted registration and KYC | When admin reviews the application | Then admin can approve or reject with reason | 1. Approval queue shows pending apps 2. KYC docs viewable inline 3. Approve triggers activation email 4. Reject triggers rejection email with reason 5. Audit log updated | 1. Admin approval queue UI 2. Document viewer 3. Approve/reject API 4. Email templates 5. Audit log write | Admin | Critical | Must | MVP | — | US-007 | Admin Dev
E03 | US-011 | Add Single Product Listing | Given I am a logged-in seller | When I fill the add product form and publish | Then the product is live on my store page | 1. Required: name, category, at least 1 image, retail price 2. Optional: wholesale price, MOQ, reel, description, variants 3. Product live within 60s of publish 4. Duplicate product name warning | 1. Product form UI 2. Multi-image upload (10 max) 3. Category selector (taxonomy) 4. Pricing fields (retail, wholesale, MOQ) 5. Variant builder 6. Publish API 7. Search index update | Seller | Critical | Must | MVP | US-012 | US-008 | Product Dev
E03 | US-012 | Edit & Archive Product | Given I have an existing product listing | When I edit product details or archive it | Then changes are reflected live within 60s | 1. All fields editable 2. Archived products hidden from customers 3. Version history for price changes 4. Bulk status change supported | 1. Edit form pre-populate 2. Archive toggle 3. Price change log 4. Bulk action API | Seller | High | Must | MVP | — | US-011 | Product Dev
E03 | US-013 | Bulk Product Import via CSV/Excel | Given I have 50+ products to list | When I upload a CSV/Excel file with product data | Then products are imported with error reporting | 1. Template CSV downloadable 2. Up to 500 products per import 3. Row-level error report shown 4. Partial import on valid rows 5. Import completes in <2 min | 1. File upload component 2. CSV parser + field mapper 3. Validation engine 4. Error report UI 5. Bulk DB insert 6. Search index bulk update | Seller | High | Should | v1.0 | — | US-011 | Backend Dev
E03 | US-014 | Product Variants (Size/Color/Weight) | Given I sell a product in multiple sizes or colors | When I define variants with separate stock and pricing | Then each variant is selectable on the product page | 1. Up to 3 variant dimensions (size, color, weight) 2. Each variant has its own stock, price override 3. Customer sees variant selector on product page 4. Out-of-stock variants grayed out | 1. Variant builder UI 2. Variant-level pricing + stock schema 3. Product page variant selector 4. Stock sync per variant | Seller | High | Must | MVP | US-019 | US-011 | Product + Backend
E03 | US-015 | Product Reel/Video Upload & Tagging | Given I want to showcase my product with a video | When I upload a reel and tag products in it | Then the reel appears on my store page and tagged products link to their pages | 1. Video up to 60s, max 100MB 2. Up to 5 products tagged per reel 3. Reel visible on store page and product pages 4. Upload completes in <90s | 1. Video upload component 2. S3 video storage + CDN 3. Product tagging UI 4. Reel–product association DB 5. Video player component on storefront | Seller | High | Should | v1.5 | — | US-011 | Content Dev
E03 | US-016 | Retail vs Wholesale Pricing Toggle | Given I sell to both retail customers and wholesale buyers | When a wholesale buyer is logged in | Then they see wholesale pricing and MOQ on product pages | 1. Wholesale price hidden from guests and retail customers 2. MOQ enforced at cart level 3. Wholesale tag visible on product card 4. Seller can enable/disable wholesale per product | 1. Customer type field (retail/wholesale) on user profile 2. Price visibility rules engine 3. MOQ cart validation 4. Product page conditional render | Seller + Customer | Critical | Must | MVP | US-019 | US-011 | Backend + Frontend
E04 | US-017 | Real-Time Stock Management | Given I have active product listings | When a product is sold or I manually adjust stock | Then inventory count updates in real time | 1. Stock decrements on order confirmation 2. Stock increments on return approval 3. Manual adjustment logs reason and timestamp 4. Negative stock not allowed | 1. Inventory service (event-driven) 2. Order→inventory deduction hook 3. Return→inventory restock hook 4. Manual adjustment API + UI 5. Adjustment audit log | Seller | Critical | Must | MVP | US-018 | US-011 | Backend Dev
E04 | US-018 | Low-Stock Alerts | Given I have set a low-stock threshold for a product | When stock falls at or below the threshold | Then I receive a push notification and email alert | 1. Threshold configurable per SKU (default: 5 units) 2. Alert fires once per breach (no spam) 3. Alert shows product name, current stock, reorder suggestion 4. Dismissable from notification centre | 1. Threshold config UI per product 2. Alert trigger logic (event-driven) 3. Push notification (FCM) 4. Email template 5. Notification centre in seller dashboard | Seller | High | Must | MVP | — | US-017 | Backend + Notif Dev
E04 | US-019 | Inventory Dashboard | Given I want an overview of my stock health | When I open the inventory dashboard | Then I see total SKUs, low-stock list, dead-stock list, and stock value | 1. Loads in <2s 2. Low-stock list sortable by urgency 3. Dead-stock = no sales in 60 days 4. Total stock value calculated at cost price | 1. Inventory summary API 2. Low-stock query (threshold breach) 3. Dead-stock query (no orders in 60 days) 4. Dashboard UI with summary cards and tables | Seller | High | Must | MVP | — | US-017 | Frontend + Backend
E05 | US-020 | Homepage Feed & Area Selector | Given I open PeteMart as a customer | When I land on the homepage | Then I see a localised feed based on my selected area | 1. Area selector defaults to geolocation or last selected 2. Featured stores show stores from selected area 3. Trending categories shown 4. Homepage loads in <2s | 1. Geolocation API integration 2. Area selector component 3. Featured stores query (by area) 4. Trending categories algorithm 5. Homepage layout + reel rail | Customer | Critical | Must | MVP | US-021 | — | Frontend + Backend
E05 | US-021 | Product & Store Typeahead Search | Given I am looking for a product or store | When I type in the search bar | Then I see relevant results within 300ms | 1. Typeahead results in <300ms 2. Results show products, stores, and categories 3. "No results" shows related suggestions 4. Search history saved locally | 1. Algolia/Elasticsearch index setup 2. Typeahead API endpoint 3. Search UI with categories 4. No-results state with suggestions 5. Search history (local storage) | Customer | Critical | Must | MVP | US-022 | US-020 | Search Dev
E05 | US-022 | Filter & Sort on Category/Search Pages | Given I am browsing a category or search results | When I apply filters (area, price, rating, stock, wholesale toggle) | Then results update instantly without page reload | 1. Filters apply in <500ms 2. Active filters shown as chips 3. Filters persist on back navigation 4. Wholesale toggle shows MOQ info | 1. Filter state management (URL params) 2. Faceted search API 3. Filter chip UI 4. Wholesale toggle integration 5. Loading skeleton on filter apply | Customer | High | Must | MVP | — | US-021 | Frontend + Search
E05 | US-023 | Store Page | Given I click on a store from search or featured | When I land on the store page | Then I see the store banner, about, social links, reel gallery, and catalog | 1. Store page loads in <2s 2. Social handle links open correct apps 3. Reel gallery shows latest 6 reels 4. Catalog filterable by category 5. WhatsApp CTA visible | 1. Store page layout 2. Social handle link handler 3. Reel gallery component 4. Catalog tab with category filter 5. WhatsApp deep link | Customer | Critical | Must | MVP | US-024 | US-008 | Frontend Dev
E05 | US-024 | Product Detail Page | Given I am viewing a product on a store page | When I open the product detail page | Then I see images, reel, pricing, stock, variants, and reviews | 1. Product page loads in <1.5s 2. Reel auto-plays muted on load 3. Wholesale price visible to eligible users 4. Out-of-stock variants grayed out 5. Reviews show average rating and last 5 reviews | 1. Product page layout 2. Image carousel 3. Reel player (muted autoplay) 4. Variant selector 5. Price visibility logic 6. Stock badge 7. Reviews component 8. Add to cart CTA | Customer | Critical | Must | MVP | US-025 | US-023 | Frontend Dev
E06 | US-025 | Multi-Store Cart | Given I want to buy from multiple stores | When I add products from different stores to cart | Then cart groups items by store with separate subtotals | 1. Items grouped by store in cart UI 2. Remove item / update quantity works per item 3. Cart persists across sessions (DB-backed) 4. Out-of-stock items flagged in cart | 1. Cart DB schema (user, store, items, qty) 2. Cart API (add, remove, update) 3. Cart UI grouped by store 4. Session persistence 5. Stock check on cart load | Customer | Critical | Must | MVP | US-026 | US-024 | Backend + Frontend
E06 | US-026 | Checkout Flow | Given I have items in my cart | When I proceed to checkout | Then I can select address, apply coupon, and review GST-inclusive total | 1. Saved addresses selectable; new address addable 2. Coupon code validation in <1s 3. GST breakdown shown per item 4. Estimated delivery date shown 5. Order summary clear before payment | 1. Address selector/add component 2. Coupon validation API 3. GST calculation engine 4. Delivery estimate logic 5. Order summary UI | Customer | Critical | Must | MVP | US-027 | US-025 | Frontend + Backend
E06 | US-027 | Razorpay Payment Integration | Given I am at the payment step | When I complete payment via UPI/card/wallet/COD | Then payment is processed and order is confirmed | 1. Razorpay checkout opens in <1s 2. UPI, cards, netbanking, wallets, COD supported 3. Payment failure shows retry option 4. COD available for orders <₹5,000 5. Payment webhook updates order status | 1. Razorpay order creation API 2. Razorpay checkout SDK integration 3. Payment webhook handler 4. COD eligibility check 5. Payment failure UI 6. Order creation on payment success | Customer | Critical | Must | MVP | US-028 | US-026 | Payments Dev
E06 | US-028 | Order Confirmation & Notifications | Given my payment is successful | When the order is confirmed | Then I receive WhatsApp + SMS confirmation with order details | 1. WhatsApp message delivered in <30s 2. SMS fallback if WhatsApp fails 3. Seller notified simultaneously 4. Order confirmation page shown in app | 1. WhatsApp Business API integration 2. SMS fallback (MSG91) 3. Seller notification trigger 4. Order confirmation page | Customer | Critical | Must | MVP | — | US-027 | Notif + Backend
E07 | US-029 | Seller Order Queue & Accept/Reject | Given a customer has placed an order | When I view my orders queue as a seller | Then I can accept or reject the order with reason | 1. New order alert (push notification) 2. Accept/reject within 30 min (auto-cancel if no action) 3. Rejection reason mandatory 4. Customer notified of rejection immediately | 1. Order queue UI (new/active/completed tabs) 2. Accept/reject API 3. Auto-cancel timer job 4. Rejection reason field 5. Customer rejection notification | Seller | Critical | Must | MVP | US-030 | US-028 | Backend + Seller Dev
E07 | US-030 | Seller Order Status Updates | Given I have accepted an order | When I update the order status (packed/dispatched/delivered) | Then the customer is notified at each stage | 1. Status update takes <2s 2. Customer gets WhatsApp + push at each stage 3. Dispatch requires tracking number or courier name 4. Delivered can be triggered by seller or auto from courier webhook | 1. Status update API 2. Status timeline UI 3. WhatsApp notification per status 4. Courier tracking field 5. Auto-delivery from courier webhook (v1.5) | Seller | Critical | Must | MVP | US-031 | US-029 | Backend + Notif
E07 | US-031 | PDF Invoice Generation | Given an order is confirmed | When I request the invoice as a seller or customer | Then a GST-compliant PDF invoice is generated | 1. Invoice includes: store logo, GST no, item details, tax breakdown, total 2. Generates in <5s 3. Downloadable and shareable via WhatsApp 4. Invoice number sequential and unique | 1. Invoice PDF template 2. PDF generation service (PDFKit/WeasyPrint) 3. S3 storage for invoices 4. WhatsApp share link 5. Sequential invoice numbering | Seller + Customer | High | Must | MVP | — | US-029 | Backend Dev
E07 | US-032 | Customer Order Tracking | Given I have placed an order | When I check my order status | Then I see a live status timeline with estimated delivery | 1. Status timeline: placed→confirmed→packed→shipped→delivered 2. Updates in real time (polling every 30s or webhook) 3. Carrier tracking link shown when dispatched 4. Estimated delivery date updated at each stage | 1. Order tracking page 2. Status timeline component 3. Real-time polling or WebSocket 4. Carrier link display | Customer | Critical | Must | MVP | US-033 | US-028 | Frontend + Backend
E07 | US-033 | Returns & Refund Request | Given I received a defective or wrong product | When I raise a return request with photo evidence | Then the seller is notified and can approve or reject the return | 1. Return window: 7 days from delivery 2. Photo upload mandatory 3. Seller has 48h to respond 4. Auto-approval if seller does not respond in 48h 5. Refund processed within 5-7 business days | 1. Return request form UI 2. Photo upload (S3) 3. Return request API 4. Seller return notification 5. Auto-approval timer job 6. Refund trigger to Razorpay | Customer + Seller | High | Must | v1.0 | — | US-032 | Backend + Payments
E08 | US-034 | Seller Sales Dashboard | Given I am a seller | When I open my analytics dashboard | Then I see today's sales, orders, AOV, and top products | 1. Dashboard loads in <2s 2. KPIs show today, last 7 days, last 30 days toggle 3. Charts rendered with Chart.js or Recharts 4. Top 5 products by revenue shown | 1. Analytics aggregation API 2. KPI calculation queries 3. Dashboard UI with KPI cards 4. Sales chart (line) 5. Top products table | Seller | Critical | Must | MVP | US-035 | US-029 | Data + Frontend
E08 | US-035 | Revenue Projection (30/60/90 Day) | Given I have at least 30 days of sales history | When I view the projection module | Then I see a 30/60/90-day revenue forecast based on trend | 1. Projection based on moving average of last 90 days 2. Confidence interval shown 3. Seasonal adjustment flag for festivals 4. Export as PDF | 1. Moving average algorithm 2. Projection chart UI 3. Festival calendar data 4. PDF export | Seller | High | Should | v1.0 | — | US-034 | Data Dev
E08 | US-036 | Product Performance Analytics | Given I want to know which products drive revenue | When I view product analytics | Then I see views, add-to-cart, orders, and revenue per SKU | 1. Funnel metrics per product: views→cart→orders 2. Conversion rate per product 3. Sortable by any metric 4. Date range filter | 1. Product event tracking (views, cart add) 2. Funnel aggregation API 3. Product analytics table UI 4. Date range picker | Seller | High | Should | v1.0 | — | US-034 | Data + Frontend
E08 | US-037 | Platform Admin Analytics | Given I am a PeteMart admin | When I open the platform analytics dashboard | Then I see GMV, orders, MRR, top areas, and top categories | 1. Real-time GMV updated every hour 2. Area-wise and category-wise breakdown 3. Customer acquisition funnel 4. Export to CSV | 1. Platform-wide aggregation queries 2. Admin analytics API 3. Admin dashboard UI 4. Area/category drill-down 5. CSV export | Admin | Critical | Must | MVP | — | US-034 | Data + Admin Dev
E09 | US-038 | Reel Upload & Product Tagging | Given I want to showcase products via short video | When I upload a reel and tag products | Then the reel is live on my store page with product links | 1. Video: max 60s, 100MB, MP4/MOV 2. Up to 5 products tagged 3. Upload + transcoding completes in <2 min 4. Reel visible on store page within 5 min of upload | 1. Video upload component 2. AWS S3 + CloudFront video delivery 3. FFmpeg transcoding pipeline 4. Product tagging UI (overlay on video) 5. Reel–product association 6. Store page reel gallery | Seller | High | Should | v1.5 | US-039 | US-015 | Content + Backend
E09 | US-039 | Social Handle Links on Store Page | Given I have linked my Instagram/WhatsApp/YouTube | When a customer visits my store page | Then they see social handle buttons that open the correct app | 1. Instagram, WhatsApp, YouTube, Facebook links supported 2. Links validated on save 3. WhatsApp opens with pre-filled "I found you on PeteMart" message 4. Links open in new tab/app | 1. Social handle form in store settings 2. URL validation per platform 3. Social button components on store page 4. WhatsApp deep link with pre-fill | Seller | High | Must | MVP | — | US-008 | Frontend Dev
E09 | US-040 | Reel Feed on Homepage | Given I am a customer on the homepage | When I scroll the reel rail | Then I see short product videos from stores in my area | 1. Reel rail shows latest 10 reels from nearby stores 2. Tap on reel opens full-screen player 3. Tagged products visible as overlay chips 4. Swipe to next reel | 1. Reel feed API (area-filtered, latest) 2. Reel rail component 3. Full-screen reel player 4. Product chip overlay 5. Swipe gesture handler | Customer | High | Should | v1.5 | — | US-038 | Frontend Dev
E10 | US-041 | Discount & Coupon Engine | Given I want to run a promotion | When I create a discount or coupon code | Then customers can apply it at checkout for the defined discount | 1. Discount types: % off, flat off, BOGO, free shipping 2. Coupon: alphanumeric code, validity dates, usage limit 3. Coupon validates in <1s at checkout 4. Usage count tracked in real time 5. Expired/exhausted coupons show clear error | 1. Promotion creation UI 2. Discount rules engine 3. Coupon validation API 4. Usage counter (Redis atomic increment) 5. Checkout integration | Seller | High | Should | v1.5 | US-042 | — | Backend + Promotions Dev
E10 | US-042 | Sponsored Listings (CPC Ads) | Given I want more visibility on PeteMart | When I create a sponsored listing campaign | Then my products appear in promoted slots on search and category pages | 1. CPC bidding: min ₹0.50/click 2. Daily budget cap settable 3. Campaign metrics: impressions, clicks, CTR, spend 4. Promoted label visible on product cards 5. Campaign pauses when budget exhausted | 1. Campaign creation UI 2. Ad auction engine 3. Promoted slot injection in search results 4. Click tracking 5. Budget deduction (real-time) 6. Campaign metrics dashboard | Seller | High | Should | v1.5 | — | US-021 | Ads + Backend Dev
E10 | US-043 | Loyalty Points & Cashback | Given I am a repeat customer | When I complete a purchase | Then I earn loyalty points redeemable on future orders | 1. 1 point per ₹10 spent 2. Points visible in account dashboard 3. Redemption: up to 20% of order value 4. Points expire after 365 days 5. Point history downloadable | 1. Points ledger DB schema 2. Points earn trigger on order delivery 3. Points redemption at checkout 4. Expiry job (nightly cron) 5. Points dashboard in customer account | Customer | Medium | Could | v2.0 | — | US-027 | Backend Dev
E11 | US-044 | Admin Merchant Directory & Search | Given I am a PeteMart admin | When I search for a merchant by name, area, or plan | Then I see a filtered list with key stats | 1. Search returns results in <1s 2. Filter by area, plan, status, join date 3. Each row shows: store name, area, plan, GMV, orders, status 4. Click-through to merchant detail | 1. Admin merchant directory API 2. Search + filter UI 3. Merchant stats aggregation 4. Merchant detail page | Admin | High | Must | MVP | US-045 | US-010 | Admin Dev
E11 | US-045 | Admin Billing & MRR Dashboard | Given I manage PeteMart finances | When I open the billing dashboard | Then I see MRR, ARR, churn, and per-merchant subscription status | 1. MRR/ARR calculated from active subscriptions 2. Churn rate = cancellations/total active in period 3. Per-merchant plan status: active, trial, overdue, cancelled 4. Overdue merchants highlighted; grace period extendable | 1. MRR/ARR/churn queries 2. Billing dashboard UI 3. Subscription status table 4. Grace period extension API | Admin | Critical | Must | MVP | — | US-009 | Admin + Data Dev
E11 | US-046 | Catalog Moderation Queue | Given a product has been flagged by a customer or algorithm | When I review it in the moderation queue | Then I can approve, reject, or request seller edit | 1. Flagged products appear in queue within 1h 2. Inline product preview 3. Approve/reject/request-edit actions available 4. Seller notified of decision 5. Audit log updated | 1. Flagging mechanism (customer report button) 2. Moderation queue API 3. Queue UI with inline preview 4. Decision API 5. Seller notification 6. Audit log | Admin | High | Should | v1.0 | — | US-011 | Admin Dev
E11 | US-047 | Dispute Resolution | Given a buyer and seller have a disagreement on an order | When an admin reviews the dispute | Then admin can override the refund or close the ticket | 1. Dispute shows buyer claim, seller response, order details 2. Admin can trigger full/partial refund override 3. Both parties notified of resolution 4. Resolution logged with admin ID | 1. Dispute detail UI 2. Admin refund override API (Razorpay) 3. Notification to both parties 4. Dispute resolution audit log | Admin | High | Should | v1.0 | — | US-033 | Admin + Payments Dev
E11 | US-048 | Homepage CMS & Banner Management | Given I want to run a seasonal campaign on PeteMart | When I upload a banner and schedule it | Then it appears on the homepage at the scheduled time | 1. Banner: JPG/PNG, max 2MB, recommended 1440x400px 2. Scheduling: start + end datetime 3. Multiple banners with priority order 4. Preview before publish 5. Auto-removes on end date | 1. Banner upload + crop UI 2. Scheduling + priority API 3. Homepage banner slot component 4. Auto-expiry job | Admin | Medium | Should | v1.0 | — | US-020 | Admin + CMS Dev
E12 | US-049 | Customer Mobile App (React Native) | Given I am a customer who prefers mobile | When I download and open the PeteMart app | Then I get the full customer experience natively on iOS and Android | 1. App available on Play Store and App Store 2. Feature parity with web: browse, cart, checkout, track, account 3. Push notifications for orders 4. Cold start in <3s 5. Offline: cached last-viewed products shown | 1. React Native project setup 2. Shared API layer with web 3. Native push notifications (FCM/APNs) 4. Offline cache (AsyncStorage) 5. App store submission 6. OTA updates (Expo/CodePush) | Customer | Critical | Could | v2.0 | — | US-027 | Mobile Dev
E12 | US-050 | Seller Mobile App (React Native) | Given I am a seller who manages my store on the go | When I open the PeteMart Seller app | Then I can manage orders, inventory, and catalog from my phone | 1. Feature parity: orders, catalog, inventory, basic analytics 2. Push alert for new orders 3. Quick stock update from inventory screen 4. Invoice PDF viewable and shareable 5. Cold start in <3s | 1. React Native seller app setup 2. Shared API layer 3. New order push alert 4. Quick stock update screen 5. Invoice viewer 6. App store submission | Seller | Critical | Could | v2.0 | — | US-029 | Mobile Dev

## Dependency Matrix
PeteMart — Story Dependency Matrix
Story ID | Story Title | Blocks | Blocked By | Dependency Type | Risk if Out of Order
US-001 | Customer OTP Login | US-019 | — | Foundation | All customer flows break
US-003 | Seller OTP Login | US-004 | US-001 | Foundation | All seller flows break
US-004 | Admin 2FA Login | — | US-001 | Foundation | Admin panel inaccessible
US-006 | Seller Registration | US-007 | US-003 | Sequential | KYC cannot start without registration
US-007 | KYC Upload | US-008 | US-006 | Sequential | Store setup blocked
US-008 | Store Profile Setup | US-009 | US-007 | Sequential | No store = no subscription
US-009 | Subscription & Payment | US-010 | US-008 | Sequential | Store not activated without payment
US-011 | Add Product | US-012, US-014, US-024 | US-008 | Foundation | No catalog = no customer browsing
US-014 | Product Variants | US-019 | US-011 | Extension | Variant stock management blocked
US-016 | Wholesale Pricing | US-019, US-025 | US-011 | Extension | B2B buyers see wrong prices
US-017 | Real-Time Inventory | US-018, US-019 | US-011 | Foundation | Overselling risk if skipped
US-020 | Homepage Feed | US-021 | — | Foundation | Discovery broken
US-021 | Typeahead Search | US-022 | US-020 | Sequential | Filters useless without search
US-023 | Store Page | US-024 | US-008 | Sequential | No store page = no product browsing
US-024 | Product Detail Page | US-025 | US-023 | Sequential | Cannot add to cart without PDP
US-025 | Multi-Store Cart | US-026 | US-024 | Sequential | Checkout blocked
US-026 | Checkout Flow | US-027 | US-025 | Sequential | Payment impossible
US-027 | Razorpay Payment | US-028 | US-026 | Critical | Revenue = 0 without this
US-028 | Order Confirmation | US-029 | US-027 | Sequential | Seller never knows about order
US-029 | Seller Order Queue | US-030, US-031 | US-028 | Sequential | Fulfillment workflow breaks
US-030 | Order Status Updates | US-032 | US-029 | Sequential | Customers get no tracking updates
US-032 | Customer Order Tracking | US-033 | US-028 | Sequential | Post-purchase experience broken
US-034 | Seller Sales Dashboard | US-035, US-036 | US-029 | Analytics | No data without orders
US-038 | Reel Upload | US-040 | US-015 | Content | Reel feed empty without uploads
US-041 | Coupon Engine | US-042 | — | Growth | Promotions impossible
US-044 | Admin Merchant Directory | US-045 | US-010 | Admin | Billing mgmt blocked
US-049 | Customer Mobile App | — | US-027 | Mobile | Full web must be stable first
US-050 | Seller Mobile App | — | US-029 | Mobile | Order management must be stable first

## RACI Chart
PeteMart — RACI Chart by Epic
R=Responsible A=Accountable C=Consulted I=Informed
Epic | Epic Name | Product Manager | Tech Lead | Frontend Dev | Backend Dev | Auth Dev | Payments Dev | Data/Analytics | Design | Admin Dev | Mobile Dev
E01 | Auth & Access | C | A | R | R | R | I | I | C | I | I
E02 | Merchant Onboarding | A | C | R | R | I | I | I | R | R | I
E03 | Product Catalog | A | C | R | R | I | I | I | R | I | I
E04 | Inventory Mgmt | A | C | I | R | I | I | I | C | I | I
E05 | Discovery & Search | A | C | R | R | I | I | I | R | I | I
E06 | Cart & Payments | A | C | R | R | I | R | I | R | I | I
E07 | Order Management | A | C | R | R | I | R | I | C | I | I
E08 | Analytics & BI | A | C | R | R | I | I | R | C | I | I
E09 | Social & Reels | A | C | R | R | I | I | I | R | I | I
E10 | Promotions | A | C | R | R | I | R | I | C | I | I
E11 | Admin & Platform Ops | A | C | I | R | I | I | R | C | R | I
E12 | Mobile Apps | A | C | I | I | I | I | I | R | I | R

## Sprint Plan
PeteMart — Sprint Plan (MVP → v1.0)
Sprint | Duration | Stories Included | Story Count | Business Impact | Goal | Team Focus | Status
Sprint 1 | Weeks 1–2 | US-001, US-002, US-003, US-004, US-005 | 5 | Critical | Auth complete for all 3 roles | Auth Dev + Backend | Not Started
Sprint 2 | Weeks 3–4 | US-006, US-007, US-008, US-009, US-010 | 5 | Critical | First seller onboarded and store live | Product Dev + Design + Payments | Not Started
Sprint 3 | Weeks 5–6 | US-011, US-012, US-014, US-016, US-017 | 5 | Critical | Seller can list products with variants, pricing, inventory | Backend + Frontend | Not Started
Sprint 4 | Weeks 7–8 | US-020, US-021, US-022, US-023, US-024 | 5 | Critical | Customer can discover and browse stores and products | Frontend + Search | Not Started
Sprint 5 | Weeks 9–10 | US-025, US-026, US-027, US-028 | 4 | Critical | End-to-end purchase flow live with Razorpay | Payments + Backend + Frontend | Not Started
Sprint 6 | Weeks 11–12 | US-029, US-030, US-031, US-032, US-018, US-019 | 6 | Critical | Order lifecycle + inventory + invoices complete | Backend + Seller Dev | Not Started
Sprint 7 | Weeks 13–14 | US-034, US-037, US-044, US-045, US-048 | 5 | High | Analytics dashboards + Admin panel MVP | Data + Admin Dev | Not Started
Sprint 8 (v1.0) | Weeks 15–16 | US-013, US-033, US-035, US-036, US-046, US-047 | 6 | High | Returns, bulk import, projections, moderation, disputes | Full Team | Not Started
Sprint 9 (v1.5) | Weeks 17–20 | US-015, US-038, US-039, US-040, US-041, US-042 | 6 | High | Reels, social handles, promotions, sponsored ads | Content + Ads Dev | Not Started
Sprint 10 (v2.0) | Weeks 21–26 | US-043, US-049, US-050 | 3 | Medium | Loyalty points + mobile apps (iOS & Android) | Mobile Dev | Not Started

## Definition of Done
PeteMart — Definition of Done (DoD)
# | Category | Criterion | Applies To | Mandatory?
1 | Code Quality | Code reviewed by at least 1 peer via pull request | All stories | Yes
2 | Code Quality | No critical or high Sentry errors in staging | All stories | Yes
3 | Code Quality | Unit test coverage ≥70% for new code | All stories | Yes
4 | Code Quality | No linting errors (ESLint/Prettier) | All stories | Yes
5 | Functionality | All acceptance criteria in the user story are met | All stories | Yes
6 | Functionality | Tested on Chrome, Firefox, Safari (web) | Frontend stories | Yes
7 | Functionality | Tested on iOS 16+ and Android 12+ (mobile) | Mobile stories | Yes
8 | Performance | Page LCP <2.5s on 4G (Lighthouse score ≥80) | Frontend stories | Yes
9 | Performance | API response P95 <200ms in staging load test | Backend stories | Yes
10 | Security | No hardcoded secrets or API keys in code | All stories | Yes
11 | Security | Authenticated endpoints reject unauthenticated requests | Auth-protected stories | Yes
12 | Accessibility | WCAG 2.1 AA: keyboard nav, alt text, contrast ratio | Frontend stories | Yes
13 | Data | DB migrations applied cleanly and reversible | DB-changing stories | Yes
14 | Data | No data loss in rollback scenario tested | DB-changing stories | Yes
15 | Payments | Payment success + failure + webhook scenarios all tested | Payment stories | Yes
16 | Notifications | WhatsApp/SMS/push notifications tested in staging | Notification stories | Yes
17 | Documentation | API endpoints documented in Postman/Swagger | Backend stories | Yes
18 | Documentation | Story marked Done in project tracker (Jira/Linear) | All stories | Yes
19 | Deployment | Deployed to staging; smoke test passed | All stories | Yes
20 | Deployment | Feature flag enabled only for internal test users until release | All stories | Yes